Strategic Direction/Goal:  Engage with a variety of stakeholders to ensure the success of OCCRRA core services as part of the Early Care and Education programs in Oklahoma.

Activity/Objective 1:  Identify specific stakeholders and determine how stakeholders can help each other by June, 2016.

| Action | Timeline | Who | Benchmarks |
| --- | --- | --- | --- |
| (Name of major action here) | (timeline) | Lead and those involved | Benchmark (measure of success) |
| Step 1. Conduct a gap analysis of OCCRRA’s services as compared to the needs of the state | By December 31, 2015 | Board, state office & regional staff | Completion of gap analysis |
| Step 2. Create an inventory of potential stakeholders with whom to start fostering relationship s | March 31, 2016 | State office & regional staff | Inventory completed |
| Step 3. Identify what successful means and create a model. | By June 30, 2016 | State office & regional staff | Model created |
| Step 4. Have an open dialogue with state level partners to recognize OCCRRA’s expertise in child care. Partners should agree on the expertise of each partner organization/agency and commit to utilizing that partner as a resource. | After plan is completed by June 30, 2017 | Executive Director | Verbal agreement at Partner meeting |

First Session: Stephanie Lippert, Facilitator, Dianne Juhnke, Mike Upton, Michelle Miller

Second Session: Dianne Juhnke, Joetta Gatliff, Brittney Wycoff, Marti Nicholson, Stephanie Lippert, Michelle Miller, Paula Koos

Strategic Direction/Goal:  Engage with a variety of stakeholders to ensure the success of OCCRRA core services as part of the Early Care and Education programs in Oklahoma.

Activity/Objective 2: Develop a matrix of board representation, analyze it and make recommendations for board composition by December 31, 2015.

| Action | Timeline | Who | Benchmarks |
| --- | --- | --- | --- |
| (Name of major action here) | (timeline) | Lead and those involved | Benchmark (measure of success) |
| Step 1. Look at by-laws to see what they currently say and what, if anything, needs to be amended. | By June 30, 2015 | Governance Committee | Existing bylaws retained or amended |
| Step 2. Identify organizations and individuals to be approached for board membership | By December 31, 2015 | Governance Committee | 2016 Board slate |

First Session: Stephanie Lippert, Facilitator, Dianne Juhnke, Mike Upton, Michelle Miller

Second Session: Dianne Juhnke, Joetta Gatliff, Brittney Wycoff, Marti Nicholson, Stephanie Lippert, Michelle Miller, Paula Koos

Strategic Direction/Goal:  OCCRRA will be seen as the leader in child care in Oklahoma.

Activity/Objective 1: Build relationships between other early childhood boards, the OCCRRA Executive Director, OCCRRA staff and OCCRRA Board by December, 2015

| Action | Timeline | Who | Benchmarks |
| --- | --- | --- | --- |
| (Name of major action here) | (timeline) | Lead and those involved | Benchmark (measure of success) |
| Step 1. Analyze Smart Start board for relationships and to determine if they have someone on their board that could be asked to sit on OCCRRA board. | By March 31, 2015 | Executive Director | Who has been added to OCCRRA board |
| Step 2. Try to get someone on Smart Start Board that understands and can speak for OCCRRA/R&R. Example: Sherry Ratcliff, Laurie Hand – both could be there representing NICCA. | By June 30, 2016 | Executive Director | Who has been added to Smart Start board |
| Step 3. Build relationship with Oklahoma Child Care Association | By September 30, 2017 | Board & Executive Director | Get invited to attend a meeting with OCCA and legislators at least once per year |
| Step 4: Review other early childhood boards (OICA, Head Start) to determine if there could be crossover between their board and the OCCRRA board. | By December 31, 2015 | Board & Executive Director | Who has been added to OCCRRA board |

First Session: Sharon Neuwald, Facilitator, Dale Wares, Karen Smith, Sharon Williams

Second Session: Dale Wares, Karen Smith, Sharon Williams, Paula Koos

Unavailable: Jennie Dexter

Strategic Direction/Goal:  OCCRRA will be seen as the leader in child care in Oklahoma.

Activity/Objective 2: Build relationships with legislature by December 2015

| Action | Timeline | Who | Benchmarks |
| --- | --- | --- | --- |
| (Name of major action here) | (timeline) | Lead and those involved | Benchmark (measure of success) |
| Step 1. Send a letter to all the new legislators welcoming them to the House/Senate and introducing OCCRRA. | By February 1, 2015 | Public Policy Committee & Community Services Manager | Letter developed and sent |
| Step 2. Utilize a 1 page sheet developed from marketing plan to take to the Capital | By March 31, 2015 | Public Policy Committee, marketing contractor, Community Services Manager & Executive Director | 1 pager developed and distributed. |
| Step 3. Identify key legislators and build relationships with those legislators | By May 31, 2015 | Board, state office & regional staff | Conversation with at least three legislators |
| Step 4. Identify linkages between important legislators and OCCRRA board members | By May 31, 2015 | Board & regional staff | Develop a chart to identify linkages |
| Step 5. Identify linkages between OCCRRA board members and lobbyists for OCCA, OICA, CSC | By September 30, 2015 | Board & Executive Director | Create a list and distribute to board for linkages |
| Step 6. Work with lobbyists to ask for an hour per week for kids bills | By November 30, 2015 | Board, Community Services Manager & Executive Director | Secure one hour of donated time per week |
| Step 7. Organize Child Watch tours to “good, bad, ugly” child care facilities in all regions | By November 30, 2017 | State office & regional staff | Number of legislators, lobbyists, community leaders and business people that attend the child watch. Number of child watch tours Training completed by all eight regions |

First Session: Sharon Neuwald, Facilitator, Dale Wares, Karen Smith, Sharon Williams

Second Session: Dale Wares, Karen Smith, Sharon Williams, Paula Koos   Unavailable: Jennie Dexter

Strategic Direction/Goal:  OCCRRA will be seen as the leader in child care in Oklahoma.

Activity /Objective 3: Develop Marketing Plan by December 2015

| Action | Timeline | Who | Benchmarks |
| --- | --- | --- | --- |
| (Name of major action here) | (timeline) | Lead and those involved | Benchmark (measure of success) |
| Step 1. Develop a 1 page sheet to give to the legislators with a crisp message | By March 1, 2015 | Executive Director, state office staff & marketing contractor | Sheet developed and distributed |
| Step 2. Develop marketing plan | By December 31, 2015 | Executive Director, state office staff & marketing contractor | Plan developed |
| Step 3. Develop a visual to take to legislators for them to identify with Resource and Referral | By November 30, 2015 | Public Policy Committee, Community Services Manager & Executive Director | Visual developed. |

Strategic Direction/Goal:  OCCRRA will be seen as the leader in child care in Oklahoma.

Activity /Objective 4: Develop Fund Raising strategy for OCCRRA by September 2015

| Action | Timeline | Who | Benchmarks |
| --- | --- | --- | --- |
| (Name of major action here) | (timeline) | Lead and those involved | Benchmark (measure of success) |
| Step 1. Identify Chair and composition of Board Development Committee | By March 31, 2015 | Board President & Board members | Board Development Committee is established |
| Step 2. Develop strategy for fund raising | By June 30, 2015 | Board & Executive Director | Written fund raising strategy |

First Session: Sharon Neuwald, Facilitator, Dale Wares, Karen Smith, Sharon Williams

Second Session: Dale Wares, Karen Smith, Sharon Williams, Paula Koos

Unavailable: Jennie Dexter

Strategic Direction/Goal: Supporting and enhancing quality care for licensed and license/exempt care through training, TA and resources.

Activities/Objective: Market and provide provider Technical Assistance (TA) toward improved quality of care by June 2016.

| Action | Timeline | Who | Benchmarks |
| --- | --- | --- | --- |
| (Name of major action here) | (timeline) | Lead and those involved | Benchmark (measure of success) |
| Step 1. Participate in planning meetings with DHS/OCCRRA/Regional Directors small group to decide on qualitative measures for contract. | By June 30, 2015 | OKDHS CCS staff, Executive Director, Parent Services Manager, regional staff | Determine qualitative measures that will meet the needs of all groups. |
| Step 2. Define the protocol for delivery of TA by regions, especially those linked to key training topics. | By March 31, 2015 | State office & regional staff | Regions will be empowered to deliver high quality, targeted, intentional technical assistance to providers that will be linked to training and result in improved quality of care. Provide Regions with a checklist for TA services. Provide regions with a checklist for services. |
| Step 3. Offer training to regional staff to deliver quality TA | By June 30, 2015 | State office staff | All regions are following the TA protocol. |
| Step 4. Create and provide marketing tools to regions to promote the availability of TA. Market and advertise TA opportunities to providers (licensing, CATTS, Community Groups, Social Media) utilizing a variety of media tools. | By December 31, 2015 | OCCRRA and Partners | Caregivers are aware of the technical assistance available to them through their local R&R. |

First Session: Marti Nicholson, Facilitator, Sheila Lynn Clark, Stephanie Makke, Keila Garcia

Second Session: Stephanie Makke, Jane Humphries, Denisia Deramus, Marti Nicholson, Stephanie Lippert, Keila Garcia, Paula Koos Unavailable: Sheila Lynn Clark

Strategic Direction/Goal: Supporting & enhancing quality care for licensed & licensed/exempt care through training, TA & resources

Activities/Objective:  Provide updated systems processes when delivering training to providers in the regions.

| Action | Timeline | Who | Benchmarks |
| --- | --- | --- | --- |
| (Name of major action here) | (timeline) | Lead and those involved | Benchmark (measure of success) |
| Step 1. Conduct a needs assessment of providers/licensing workers to see what they perceive as the training needs. | By June 30, 2015 And repeated every two years | State office staff compiles & regional staff distribute. | Needs of providers in communities served will be determined in order to plan training to be offered. |
| Step 2. Organize existing training offerings by core competencies, age group, and topic. | By December 31. 2015 | Parent Services Manager, Hispanic Services Coordinator & Database Coordinator | The framework will list offerings by age group, topic and core competencies. |
| Step 3. Select two key topics for training to be offered by all regions, linked to onsite technical assistance. | By September 30, 2015 | State office & regional staff | Regions will be empowered to offer high quality training to providers that advances the professional development of providers. |
| Step 4. Conduct two “train the trainer” sessions for regional staff on content when presenting key topics. | By March 31, 2016 | State office staff | At least 80% of regional staff wo conduct training on key topics will have attended a “train the trainer” session. |

First Session: Marti Nicholson, Facilitator, Sheila Lynn Clark, Stephanie Makke, Keila Garcia

Second Session: Stephanie Makke, Jane Humphries, Denisia Deramus, Marti Nicholson, Stephanie Lippert, Keila Garcia, Paula Koos

Unavailable: Sheila Lynn Clark